## Checklist
Contents (as requested by LGU c/o Anamher)
Number | Item | Development Status | Priority | Date Raised | Date Completed | Notes | Reference Document(s) | Coverage / Gaps
1 | Cicha | Raised | [5 empty] | NO DOCUMENT. "Cicha" — clarify with LGU (Citizen's Charter? a person/section name?). If Citizen's Charter: already covered by assets/contents/Citizen's Charter 2023.pdf (already parsed into data/citizens-charter.json)
2 | Contact | Raised |  |  |  |  | MDRRMO_Municipal Emergency Hotline Calatrava.docx; MEO_Municipal Engineer Profile (Portrait and Office Contact).docx; MNAO_Office Profile and Weight for Age CY2026.docx; OMAG_… (letterhead: maocalatrava@gmail.com); MDRRMO_… (letterhead: drrmcalatrava@gmail.com) | PARTIAL. Have: 4 emergency hotlines (Emergency Command Center, PNP, BFP, RHU), MEO office number, MNAO officer/staff numbers, OMAG + MDRRMO emails from letterheads. Missing: main trunkline, Mayor's Office email/phone, per-office directory for the other offices.
3 | Organizational | Raised |  |  |  |  | assets/contents/Organizational Chart 2026.pptx (already parsed into data/organization.json) | COVERED by existing org chart. No new document in this batch. MNAO doc adds the Municipal Nutrition Committee composition; OMAG doc adds OMAG staff list.
4 | Vision | Raised |  |  |  |  | MSWDO_Vision Mission and Services Offered.pdf; MASSO_Mandate Vision Mission and Services.docx; MBO_Mandate Vision Mission MFO and Targets CY2027 (LBP Form 4).pdf; MEO_Mandate Vision Mission MFO and Targets CY2027 (LBP Form 4).pdf; MNAO_Office Profile and Weight for Age CY2026.docx | PARTIAL. Have office-level Vision for MSWDO, MASSO, MBO, MEO, MNAO. Missing: MUNICIPAL vision (LGU-wide) — already on the site from officials.json; confirm with Mayor's Office. Missing office visions: BPLO, OMAG, MCR, MPDO, MDRRMO, KALAHI.
5 | Mission | Raised |  |  |  |  | (same as Vision) | PARTIAL. Same 5 offices as Vision. Municipal mission not in this batch.
6 | Pledge | Raised | [5 empty] | NO DOCUMENT. Pledge (service pledge / ARTA pledge) not supplied. The Citizen's Charter 2023 usually carries a Service Pledge page — check assets/contents/Citizen's Charter 2023.pdf (already parsed into data/citizens-charter.json)
7 | Mandate per office may mandates | Raised |  |  |  |  | BPLO_Mandate Key Functions and Services Offered.docx; MASSO_Mandate Vision Mission and Services.docx; MBO_… (LBP Form 4).pdf; MEO_… (LBP Form 4).pdf | PARTIAL. Explicit "Mandate" text for BPLO, MASSO, MBO, MEO only. Other offices gave services/profiles but no mandate statement (MSWDO, MNAO, OMAG, MDRRMO, MCR, KALAHI). Missing entirely: MPDO, Treasurer, Accountant, MHO, SB, Mayor's Office, HRMO.
8 | Brief History | Raised | [5 empty] | NO DOCUMENT. Brief History not supplied; site currently uses placeholder history in officials.json.
9 | FDP(Full Disclosure Policy) | [5 empty] | MDRRMO_LDRRMF Utilization Reports Jan-Jul 2026 (FDP Form 8).pdf; GFPS_Annual GAD Accomplishment Report CY2025 (FDP Form 5).xlsx; MBO_Supplemental Budgets Nos 1-4 CY2025 (SB Appropriation Ordinances).pdf | PARTIAL. Have FDP Form 5 (GAD AR 2025), FDP Form 8 (LDRRMF Jan–Jul 2026, 7 monthly reports), and the 4 CY2025 supplemental budget ordinances. Missing FDP forms: Annual Budget (Form 1), Quarterly Statement of Cash Flows, SRE, Trust Fund utilization, 20% DF utilization, SEF, Bid results / procurement (Forms 9–12), Annual Procurement Plan, Manpower complement, Unliquidated cash advances, Items to be bid.
10 | CLUP | [6 empty] | NO DOCUMENT. CLUP not supplied (OMAG doc cites "source CLUP" for the 5,987.502 ha agricultural land figure, so a CLUP exists).
11 | Annual Budget | [5 empty] | MBO_Supplemental Budgets Nos 1-4 CY2025 (SB Appropriation Ordinances).pdf; GFPS_Annual GAD Plan and Budget FY2027.xlsx (states Total LGU Budget FY2027 = ₱157,082,776.00); GFPS_Annual GAD Accomplishment Report CY2025 (states Total LGU Budget 2025 = ₱119,561,203) | PARTIAL. Have only SUPPLEMENTAL budgets for 2025 (Nos. 1–4: ₱5,685,654.07 / ₱43,075,620.88 / ₱1,012,360.13 / ₱1,808,000.00). Missing: the Annual Budget ordinance itself (CY2025 and CY2026), and the Annual Investment Program.
12 | LDIP(Local Development Investment Plan) | [6 empty] | NO DOCUMENT. LDIP not supplied. (MEO LBP Form 4 lists 20% Development Fund PPAs for 2027 — a partial proxy for infrastructure, not the LDIP.)
(Offices)
13 | MPDO | [6 empty] | NO DOCUMENT. MPDO submitted nothing in this batch. The Citizen's Charter has MPDO's Locational Clearance/Zoning service (pp. 17–21).
14 | MDRRMO | [5 empty] | MDRRMO_Municipal Emergency Hotline Calatrava.docx; MDRRMO_LDRRMF Utilization Reports Jan-Jul 2026 (FDP Form 8).pdf | PARTIAL. Have: hotlines, MDRRMO logo (in the hotline .docx), letterhead email, LDRRMF utilization. Missing: MDRRMO mandate/vision/mission, staff, programs, evacuation centers, hazard maps.
15 | MAss (Municipal Assessor) | [5 empty] | MASSO_Mandate Vision Mission and Services.docx | COVERED (text). Mandate, vision, mission, 7 services. Citizen's Charter pp. 38–45 has the 3 charter services with fees/steps. Missing: staff list, contact.
16 | KALAHI | [5 empty] | KALAHI_Philippine Community Resilience Project (PCRP) Overview.docx | COVERED (program overview). PCRP/KALAHI-CIDSS overview, principles, components, ₱70M 3-year grant schedule 2026–2029, eligible/ineligible sub-projects, logo + infographics. Missing: Calatrava-specific sub-project list, MResT/ACT staff, contact.
17 | Engineering | [5 empty] | MEO_Mandate Vision Mission MFO and Targets CY2027 (LBP Form 4).pdf; MEO_Municipal Engineer Profile (Portrait and Office Contact).docx; MEO_Permits/ (13 NBC permit forms); MEO_Citizens Charter 2023 pp64-67 … (DUPLICATE) | COVERED. Mandate, vision, mission, 2027 PPAs incl. 20% DF projects, engineer portrait + office number, 13 downloadable permit application forms. Note: Unified Building Permit form still says "CITY/MUNICIPALITY OF CEBU" in the Location of Construction line — LGU should fix before publishing.
18 | Agriculture | [5 empty] | OMAG_Office Profile Agricultural Statistics and Programs.docx | PARTIAL. Staff (6), agricultural statistics (7 figures), 12 programs/services, letterhead email. Missing: the "List of Registered Farmers and Fisherfolk Organizations" — heading is in the doc but the list itself was not included. No mandate/vision/mission.
19 | Budget | [5 empty] | MBO_Mandate Vision Mission MFO and Targets CY2027 (LBP Form 4).pdf; MBO_Supplemental Budgets Nos 1-4 CY2025 (SB Appropriation Ordinances).pdf | COVERED (office). Mandate (5 items), vision, mission, 2027 budget management program targets. Citizen's Charter pp. 62–64 has the 2 MBO services.
20 | MCR (Municipal Civil Registrar) | [5 empty] | MCR_Citizens Charter 2023 pp21-26 Civil Registry Services (DUPLICATE).pdf | ALREADY ON SITE. MCR sent pages 21–26 of the Citizen's Charter (5 services) which are already in data/citizens-charter.json. Missing: MCR mandate/vision/mission, staff, contact.
21 | Punong Brgys(Contact details at email add) | [5 empty] | MNAO_Office Profile and Weight for Age CY2026.docx (7 barangay seals embedded as images; BNS per barangay) | PARTIAL. No Punong Barangay contact details / emails were supplied. The MNAO doc incidentally contains all 7 official barangay seals (Talisay, Poblacion, Pagsangahan, Linao, San Roque, Pangulo, Balogo) — usable for barangays.html.
22 | Municipal Nutrition Action Office (MNAO) | [5 empty] | MNAO_Office Profile and Weight for Age CY2026.docx | COVERED. Vision, mission, officer + staff with mobile numbers, Municipal Nutrition Committee (16 members), 7 Barangay Nutrition Scholars (Poblacion vacant), Weight-for-Age CY2026 table (900 children: 92.56% normal). Missing: mandate, programs list.
23 | BPLO | [5 empty] | BPLO_Mandate Key Functions and Services Offered.docx | COVERED (text). Mandate, 4 key functions, 6 services. Citizen's Charter pp. 7–11 has the business-permit procedure. Missing: staff, contact, vision/mission.
24 | MSWDO | [5 empty] | MSWDO_Vision Mission and Services Offered.pdf (scanned, 2 pp.) | COVERED. Vision, mission, 5 services, requirements for medical/burial/fire/social-case-study/VAWC/PMC, livelihood programs, solo parent / PWD / senior citizen registration requirements. Missing: mandate, staff, contact. Note: scanned image — will need re-typing.
25 | GAD (GFPS) — not in original list | [5 empty] | GFPS_Annual GAD Accomplishment Report CY2025 (FDP Form 5).xlsx; GFPS_Annual GAD Plan and Budget FY2027.xlsx | RECEIVED, unrequested. Both are FDP-postable documents (GAD AR is FDP Form 5). Belongs under item 9 (FDP) on the site. GPB 2027 workbook also has a "Barangay" sheet and scratch sheets (Sheet1–3) — only the PCM sheet is the actual form.
Reference documents live in assets/reference docs/ (renamed Dept_DocName). Files marked (DUPLICATE) re-send content already parsed into the site. See assets/reference docs/README.md for the full audit.

## Feedback
Number | Summary | Date Raised | Date Completed | Development Status | Notes
1
2
3
4